9A | UP ZONE-1 | UTTAR PRADESH | 9 | 941A | CHITRAKOOT | 944 | KAUSHAMBI | 94401A | MANJHANPUR | 94405 | SARSAWAN | 94405040 | RAKSOULI | EGE4492 | Neeraj Garg | RAKSOULI | Submitted for Approval | 28/02/2025 | GKP ( Full Day ) | COMPOSIT SCHOOL RAKSHULI | GKP | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92303A | DHAURAHARA | 92303 | DHAURAHARA | 92303034 | WALI | EGE8749 | Lalit Kumar | DIHUWAPURKALAN | Approved | 19/02/2025 | D2D Contact ( First Half ) |  | D2D Contact | 6 | No | No | 19/02/2025 | GKP Bal Sabha & LSE |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 970A | ROBERTSGANJ | 969 | MIRZAPUR | 97005A | CHATRA | 96906 | RAJGARH | 96909120 | GHATAMPUR | EGE5903 | Anita Kumari | KOLANA | Approved | 25/02/2025 | GKP ( Full Day ) | P.S. KOLNA-2 | GKP | 0 | No | No | 25/02/2025 | GKP |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92513A | SANDI | 92504 | SURSA | 92504101 | TIKRI | EGE8086 | Satyam Singh | BAHRAIA | Approved | 21/02/2025 | GKP ( Second Half ) | PRY.SCH. BAHARAIA | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92507A | BABAN | 92507 | BABAN | 92507041 | MUJAHIDPUR | EGE8085 | Arun Kumar | BEHATA GOKUL | Approved | 06/03/2025 | GKP ( Full Day ) | PRY. SCH. BEHATA GOKUL | GKP | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 929 | FARRUKHABAD | 92903A | NAWABGANJ | 92901 | KAIM GANJ | 92901141 | SUBHANPUR | EGE8713 | Shikha Katiyar | NIZAMUDDINPUR | Approved | 06/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 10 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232412B | RANAPUR | 232412 | RANAPUR | 232412049 | BUDHASHALA | SMP261 | Pramod Kumar Meda | BHANDAKHEDA | Submitted for Approval | 21/02/2025 | Enrolment ( First Half ) | GOVT P S BHANDAKHEDA | Enrolment | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92309A | NIGHASAN | 92309 | NIGHASAN | 92309080 | CHAKHARA | EGE8527 | Poonam Devi | DUBAHA | Approved | 24/02/2025 | GKP ( Full Day ) | PRI.SCH. DUBAHA | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92203A | JALALABAD | 92203 | JALALABAD | 92203141 | SARAY SAUDHO | EGE8348 | Kunal Mishra | TAPAR | Approved | 03/03/2025 | GKP ( Full Day ) | P.S.TAPAR | GKP | 0 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2349A | ALIRAJPUR | 2349 | ALIRAJPUR | 234905A | UDAYGARH | 234901 | JOBAT | 234901016 | JALI | SMP213 | PRAKASH CHOUHAN | BADI JUWARI | Approved | 17/02/2025 | GKP ( Full Day ) | GURAD F KIKRIYA F BADI DUWARI | GKP | 0 | No | No | 17/02/2025 | Enrolment |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 929 | FARRUKHABAD | 92903A | NAWABGANJ | 92904 | KAMALGANJ | 92901116 | KAMRUDDIN NAGAR | EGE8976 | Arjeet Singh | EKALAHARA | Approved | 24/02/2025 | GKP ( First Half ) | PS EKLAHRA | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92503A | BEHANDAR | 92503 | BEHANDAR | 92503012 | KAHACHARI | EGE8095 | Shivam | KAHACHARI | Approved | 25/02/2025 | GKP ( Full Day ) | PRY. SCH. KAHACHARI | GKP | 0 | No | No |  |  |  | Red
9B | UP ZONE-2 | UTTAR PRADESH | 9 | 924A | SITAPUR | 924 | SITAPUR | 92416A | RAMPURMATHURA | 92416 | RAMPURMATHURA | 92416100 | ATORA | EGE8269 | Pawan Kumar Verma | KANRAKHI | Submitted for Approval | 05/03/2025 | GKP ( Full Day ) | UPS KANARKHI COMPOSITE (1TO8) | GKP | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92505A | SANDILA | 92505 | SANDILA | 92505009 | SOM | EGE8107 | Madhuri Pal | JAMSARA | Approved | 24/02/2025 | GKP ( Full Day ) | PRY.SCH. BHOLAKHEDA | GKP | 0 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2329A | KHANDWA | 2348 | BURHANPUR | 234805A | KHAKNAR | 234805 | KHAKNAR | 234805002 | AMBADA RAIYAT | SMP174 | Anil Rathod | BADA JAINABAD | Approved | 24/02/2025 | GKP ( Full Day ) | PS BADA TANDA | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92509A | TANDIYAWA | 92501 | HARIYAWAN | 92501027 | KALIYANI | EGE8092 | Sobhit Kumar | LEHANA | Approved | 03/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 10 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92310A | NAKAHA | 92310 | NAKAHA | 92310029 | RANGEELA NAGAR | EGE8917 | Anuradha | BEDANA PUR | Approved | 18/02/2025 | GKP ( Second Half ) | PS BEDANAPUR | GKP | 0 | Yes | Yes | 18/02/2025 | GKP |  | Green
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232408B | JHABUA-2 | 232408 | JHABUA | 232408151 | UMARIYA VEJANTRI | SMP241 | RAVI BARIYA | PITHANPUR | Approved | 27/02/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 3 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92505A | SANDILA | 92505 | SANDILA | 92505074 | BEGAM GANJ | EGE8067 | Upasana Yadav | SARWA | Approved | 07/03/2025 | GKP ( Full Day ) | PRY. SCH. SARWA | GKP | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92206A | BANDA | 92206 | BANDA | 92206039 | NAVICHI | EGE8277 | Rohit Bhardwaj | PATTI CHHAJJUPUR | Approved | 17/02/2025 | GKP ( Second Half ) | COMPOSITE PATTI CHHAJJUPUR | GKP | 0 | Yes | Yes | 17/02/2025 | GKP MM |  | Green
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 970A | ROBERTSGANJ | 969 | MIRZAPUR | 96902A | HALIA | 96902 | HALIA | 96902162 | BELGAWAN | EGE7126 | Ravi Kumar | BHAISOR BALAY PAHAD | Submitted for Approval | 28/02/2025 | Bal Sabha & LSE ( First Half ) | U.P.S. BHAISODBALAY PAHAD | Bal Sabha & LSE | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92303A | DHAURAHARA | 92303 | DHAURAHARA | 92303005 | GUDARIYA | EGE8900 | Pooja Raj | RASULPUR 1 | Approved | 20/02/2025 | GKP ( First Half ) | PRI. SCH. RASUL PUR | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92204A | NIGOHI | 92204 | NIGOHI | 92204067 | UDARA | EGE8111 | Arjun Rathour | BASARI | Approved | 17/02/2025 | GKP ( Full Day ) | P.S.BASARI | GKP | 0 | Yes | Yes | 17/02/2025 | GKP |  | Green
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 971 | BHADOHI | 97102A | GYANPUR | 97101 | BHADOHI | 97101227 | BADI | EGE7665 | Vijay Kumar Yadav | AJAYPUR | Approved | 27/02/2025 | Bal Sabha & LSE ( First Half ) | UPS AJAYPUR | Bal Sabha & LSE | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92202A | JAITIPUR | 92217 | MADNAPUR | 92217091 | BARI KHAS | EGE8114 | Akshita Pandey |  | Approved | 19/02/2025 | Meeting ( Second Half ) |  | Meeting | 0 | No | No | 19/02/2025 | GKP |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2349A | ALIRAJPUR | 2349 | ALIRAJPUR | 234906A | SONDWA | 234906 | SONDWA | 234906059 | UMRALI | SMP212 | HIRALAL SOLANKI | DABADI | Approved | 27/02/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 15 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2349A | ALIRAJPUR | 2349 | ALIRAJPUR | 234907A | CHANDRA SHEKHAR AZAD NAGAR | 234907 | CHANDRA SHEKHAR AZAD NAGAR | 234907031 | RINGOLE | SMP190 | SOHAN SINGH BHABAR | RINGOLE | Approved | 17/02/2025 | GKP ( Full Day ) | P S MALMASOORI | GKP | 0 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232408B | JHABUA-2 | 232408 | JHABUA | 232408042 | AMLI FALIYA | SMP303 | RAMILA GUNDIYA | AMLI FALIYA | Approved | 25/02/2025 | GKP ( Full Day ) | PS RATNA F AMALIFALIYA | GKP | 0 | No | No |  |  |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 971 | BHADOHI | 97102A | GYANPUR | 97104 | AURAI | 97102121 | LAKHANO | EGE6351 | Dashrath Prajapati | SARIPUR | Approved | 26/02/2025 | GKP ( First Half ) | P S SARIPUR 1 | GKP | 0 | No | No | 26/02/2025 | MM |  | Red
9B | UP ZONE-2 | UTTAR PRADESH | 9 | 924A | SITAPUR | 924 | SITAPUR | 92403A | BISWAN | 92403 | BISWAN | 92403099 | BHAGIPUR | EGE8463 | Surendra Kumar | KARIMPANAH | Approved | 05/03/2025 | GKP ( Full Day ) | UPS KARIM PANAH COMPOSITE (1TO8) | GKP | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92210A | KALAN | 92210 | KALAN | 92210077 | BHUNNI KHERA | EGE9159 | Shivam Mishra | GATHIYA CHHABI | Submitted for Approval | 05/02/2025 | Bal Sabha & LSE ( Full Day ) | COMPOSIT GADIYA CHHABI | Bal Sabha & LSE | 0 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232412B | RANAPUR | 232412 | RANAPUR | 232412049 | BUDHASHALA | SMP261 | Pramod Kumar Meda | KANJAWANI | Submitted for Approval | 19/02/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 15 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 919A | BUDAUN | 919 | BUDAUN | 91902A | UJHANI | 91902 | UJHANI | 91902035 | SARKI | EGE8191 | Rajat Kumar Gautam | MEERA SARAI | Submitted for Approval | 17/02/2025 | GKP ( First Half ) | PS. MEERA SARIA | GKP | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92310A | NAKAHA | 92310 | NAKAHA | 92310060 | NIJAMPUR NIKATI | EGE8820 | Amit Kumar Singh | BAJUDIHA | Approved | 26/02/2025 | GKP ( First Half ) | PRI.SCH.BAJUDIHA | GKP | 0 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232404A | THANDLA | 232404 | THANDLA | 232404087 | DEVGARH | SMP277 | Dal Sing | DEVGARH | Approved | 25/02/2025 | GKP ( First Half ) | NMS DEVGARH | GKP | 0 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232404A | THANDLA | 232404 | THANDLA | 232404005 | SUJAPURA | SMP283 | Vagmal Muniya | RATNALI | Approved | 14/02/2025 | GKP ( First Half ) | PS RATNALI | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 919A | BUDAUN | 919 | BUDAUN | 91901A | QADARCHOWK | 91901 | QADARCHOWK | 91909055 | NAULIFATUHABAD | EGE8366 | Mujassim Be | TATAR PUR | Submitted for Approval | 18/02/2025 | GKP ( First Half ) | PS. TATAAR PUR | GKP | 0 | Yes | Yes | 18/02/2025 | GKP
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92303A | DHAURAHARA | 92304 | ISANAGAR | 92304013 | BELTUA | EGE9194 | Diksha Pandey | MURI | Approved | 18/02/2025 | GKP ( Second Half ) | UPS MOODI COMPOJIT(1 To 8) | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92516A | KACHAUNA | 92516 | KACHAUNA | 92516064 | SHIVPURI | EGE8306 | Gyanendra Kumar Singh | PURWA | Approved | 17/02/2025 | MM ( Full Day ) |  | MM | 0 | Yes | No | 17/02/2025 | GKP MM |  | Green
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92510A | TONDARPUR | 92510 | TONDARPUR | 92510046 | ANJHI | EGE9073 | Akarshit Panday | NEWADA CHATHIYA | Approved | 21/02/2025 | GKP ( Full Day ) | PRY. SCH. NEWADA CHATHIYA | GKP | 0 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232411A | MEGHNAGAR | 232411 | MEGHNAGAR | 232411026 | CHENPURA | SMP271 | Sumitra Maida | RAJPURA | Submitted for Approval | 18/02/2025 | GKP ( Full Day ) | GOVT M.S. RAJPURA | GKP | 0 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232404A | THANDLA | 232404 | THANDLA | 232404081 | KAKANWANI | SMP281 | Raju Katra | NAVAPADA | Approved | 06/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 5 | No | No
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 970A | ROBERTSGANJ | 970 | SONBHADRA | 97001A | CHOPAN | 97001 | CHOPAN | 97001020 | ADALGANJ (SINDURIYA) | EGE7834 | Rinki | KARGARA | Approved | 27/02/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 2 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92516A | KACHAUNA | 92516 | KACHAUNA | 92516025 | MUSALMANABAD | EGE8493 | Sandeep Kumar | MUSALMANABAD | Approved | 28/02/2025 | D2D Contact ( Second Half ) |  | D2D Contact | 5 | No | No | 28/02/2025 | Enrolment |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92506A | AHIRORI | 92506 | AHIRORI | 92506065 | BHITHA MAHASINGH | EGE8311 | Sadhana Devi | MANGOLA PUR | Approved | 05/03/2025 | Bal Sabha & LSE ( First Half ) | JHS. MANGOLAPUR | Bal Sabha & LSE | 0 | No | No
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 941A | CHITRAKOOT | 940 | BANDA | 94004A | NARAINI | 94004 | NARAINI | 94004009 | HADHAMAFI | EGE4235 | Ashish Kumar Gupta | CHANDOR | Submitted for Approval | 24/02/2025 | MM ( Full Day ) |  | MM | 0 | No | No | 24/02/2025 | GKP
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2329A | KHANDWA | 2348 | BURHANPUR | 234805A | KHAKNAR | 234805 | KHAKNAR | 234805063 | KHAKNAR KHURD | SMP169 | Sandip Pawar | DOIFORIA | Approved | 26/02/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 10 | No | No |  |  |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 941A | CHITRAKOOT | 940 | BANDA | 94004A | NARAINI | 94003 | MAHUWA | 94003050 | BAHERI | EGE4468 | RAMNARESH | HASTAM | Submitted for Approval | 28/02/2025 | GKP ( Full Day ) | UP S HASTAM | GKP | 0 | No | No
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 945 | PRAYAGRAJ | 94502A | KAUNDHIYARA | 94503 | JASARA | 94513066 | CHAK ABHAY RAM | EGE5216 | Ajay Kumar | TIGNAUTA | Approved | 25/02/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 5 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92518A | BHARAWAN | 92518 | BHARAWAN | 92518017 | GONI | EGE8488 | Preeti Chaudhari | DHIKUNNI | Approved | 21/02/2025 | GKP ( Full Day ) | PRY. SCH. DHIKUNNI | GKP | 0 | Yes | Yes | 21/02/2025 | GKP |  | Green
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92303A | DHAURAHARA | 92304 | ISANAGAR | 92304013 | BELTUA | EGE9194 | Diksha Pandey | BELTUA | Approved | 08/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 20 | No | No
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 971 | BHADOHI | 97107A | ABHOLI | 97103 | SURIYAVAN | 97105101 | CHANDA PUR | EGE6079 | Satyendra Kumar Singh | DARVANSI | Approved | 17/02/2025 | GKP ( Full Day ) | P S DARVANSI 1 | GKP | 0 | No | No | 17/02/2025 | GKP Bal Sabha & LSE |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 970A | ROBERTSGANJ | 969 | MIRZAPUR | 96902A | HALIA | 96902 | HALIA | 96902162 | BELGAWAN | EGE7126 | Ravi Kumar | SONGARHA | Submitted for Approval | 27/02/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 10 | No | No
9B | UP ZONE-2 | UTTAR PRADESH | 9 | 924A | SITAPUR | 924 | SITAPUR | 92418A | SAKARAN | 92418 | SAKARAN | 92418027 | SULTANPUR | EGE8255 | Ankit Kumar | KANKAR KUI | Approved | 04/03/2025 | GKP ( Full Day ) | P.S KANKAR KUI | GKP | 0 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2328A | BARWANI | 2328 | BARWANI | 232804 | PATI | 232804 | PATI | 232804080 | AWALI | EGE6394 | Tikaram Dodawe | DERVALIYA | Submitted for Approval | 18/02/2025 | GKP ( Full Day ) | UEGS DAGADGHATI FALYA DERVALIYA | GKP | 0 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232408B | JHABUA-2 | 232408 | JHABUA | 232408042 | AMLI FALIYA | SMP303 | RAMILA GUNDIYA | AMLI FALIYA | Approved | 03/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 2 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2349A | ALIRAJPUR | 2349 | ALIRAJPUR | 234903A | KATTHIWARA | 234903 | KATTHIWARA | 234903047 | KAVACHHA | SMP200 | GOVIND TOMAR | KAVACHHA | Approved | 24/02/2025 | Enrolment ( First Half ) | KPS DABCHA F. KAVCHHA | Enrolment | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92518A | BHARAWAN | 92518 | BHARAWAN | 92518004 | SIKANDAR PUR | EGE9179 | Rohini Tiwari | KAURIA | Approved | 21/02/2025 | GKP ( Full Day ) | PRY. SCH. KAURIA 1 | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 919A | BUDAUN | 919 | BUDAUN | 91906A | JAGAT | 91906 | JAGAT | 91906053 | SOBHAN PUR | EGE8791 | Vipin | LAKHAN PUR | Submitted for Approval | 07/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 25 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232408A | JHABUA-1 | 232408 | JHABUA | 232408017 | KHEDI | SMP229 | Gammu Singh Bhabor | KHEDI | Submitted for Approval | 26/02/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 10 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 929 | FARRUKHABAD | 92903A | NAWABGANJ | 92904 | KAMALGANJ | 92901116 | KAMRUDDIN NAGAR | EGE8976 | Arjeet Singh | EKALAHARA | Approved | 19/02/2025 | D2D Contact ( Second Half ) |  | D2D Contact | 10 | No | No | 19/02/2025 | GKP |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92314A | PASGAWAN | 92314 | PASGAWAN | 92308024 | SARELI | EGE8757 | Munesh Kumar | SARELI | Submitted for Approval | 04/03/2025 | Bal Sabha & LSE ( Full Day ) | PMV.SARELI | Bal Sabha & LSE | 0 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2349A | ALIRAJPUR | 2349 | ALIRAJPUR | 234906A | SONDWA | 234906 | SONDWA | 234906059 | UMRALI | SMP212 | HIRALAL SOLANKI | UMRALI | Approved | 28/02/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 15 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92307A | MOHAMMADI | 92305 | KUMBHI-GOLA | 92305087 | MURA JAWAHAR | EGE8532 | Anuj Kumar Varma | DHIRAVAN | Approved | 17/02/2025 | GKP ( Full Day ) | PRI.SCH. DHIRANVA | GKP | 0 | Yes | Yes | 17/02/2025 | GKP |  | Green
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92313A | RAMIYA BEHAR | 92313 | RAMIYA BEHAR | 92313047 | RAMNAGAR BAGAHA | EGE8529 | Pavan Kumar | KRISHNA NAGAR COLONY | Approved | 21/02/2025 | Bal Sabha & LSE ( Second Half ) | UPS KRISHNANAGAR COLONY COMPOJIT(1 To 8) | Bal Sabha & LSE | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 929 | FARRUKHABAD | 92903A | NAWABGANJ | 92903 | NAWABGANJ | 92903082 | GUTHINA | EGE8316 | Rohit Yadav | SHIVRAI MATH | Approved | 28/02/2025 | GKP ( Full Day ) | PS SHIVRAI MATH | GKP | 0 | No | No |  |  |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 970A | ROBERTSGANJ | 969 | MIRZAPUR | 96910A | MAJHAWA | 96909 | NARAYANPUR | 96909081 | NARAYANPUR | EGE8967 | Ram Chandra | BABHANEE | Approved | 17/02/2025 | Bal Sabha & LSE ( First Half ) | COMPOSIT SCHOOL BABHANEE | Bal Sabha & LSE | 0 | Yes | Yes | 17/02/2025 | Bal Sabha & LSE |  | Green
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232408A | JHABUA-1 | 232408 | JHABUA | 232408014 | AMALI PATHAR | SMP226 | Balram Damor | LOHARIYA | Submitted for Approval | 11/02/2025 | Enrolment ( Second Half ) | P S LOHARIYA | Enrolment | 0 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232410 | RAMA | 232410 | RAMA | 232410017 | DOCHHKA | SMP249 | Prakash Sangod | DOCHHKA | Approved | 20/02/2025 | Enrolment ( Full Day ) | GOVT. HS DHOCHKA | Enrolment | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92208A | TILHAR | 92208 | TILHAR | 92208035 | KHANDSAR | EGE8332 | Bheem Pratap | MILKIPUR | Approved | 20/02/2025 | D2D Contact ( Second Half ) |  | D2D Contact | 10 | No | No | 20/02/2025 | Bal Sabha & LSE |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 941A | CHITRAKOOT | 944 | KAUSHAMBI | 94401A | MANJHANPUR | 94401 | MANJHANPUR | 94401019 | GUWARA TAYABPUR (DHARMPUR) | EGE4213 | MOHAN LAL | RAHIMPUR MOLANI | Submitted for Approval | 05/03/2025 | GKP ( First Half ) | P.S. RAHIMPUR MOLANI | GKP | 0 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232412B | RANAPUR | 232412 | RANAPUR | 232412061 | LAMBELA | SMP260 | Mukesh Bhuriya | KAKARADRA (KUNDANPUR) | Approved | 04/03/2025 | GKP ( Full Day ) | GOVT PS MANGA F KAKRADARA | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92310A | NAKAHA | 92310 | NAKAHA | 92310015 | NAKAHA | EGE8762 | Arti Gupta | NAKAHA | Approved | 24/02/2025 | GKP ( First Half ) | PRI.SCH.NAKAHA | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 929 | FARRUKHABAD | 92906A | BARH PUR | 92908 | MOHAMDABAD | 92905032 | KUBERPURKUTLUPUR | EGE8497 | Shivendra Mishra | GUDERA | Approved | 22/02/2025 | GKP ( Full Day ) | PS GUDERA | GKP | 0 | No | No |  |  |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 945 | PRAYAGRAJ | 94504A | PRATAP PUR | 94504 | PRATAP PUR | 94506059 | VEER KAJI | EGE7465 | Vimla Bind | VEER KAJI | Approved | 25/02/2025 | GSS ( Full Day ) |  | GSS | 0 | Yes | No | 25/02/2025 | GSS |  | Green
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92503A | BEHANDAR | 92503 | BEHANDAR | 92503032 | JAHIDPUR | EGE8076 | Paras Nath Shukla | BIRAULI | Approved | 24/02/2025 | GKP ( Full Day ) | Composite School BIRAULI | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92206A | BANDA | 92206 | BANDA | 92206039 | NAVICHI | EGE8277 | Rohit Bhardwaj | PATTI CHHAJJUPUR | Approved | 19/02/2025 | GKP ( Full Day ) | COMPOSITE PATTI CHHAJJUPUR | GKP | 0 | Yes | Yes | 19/02/2025 | GKP Bal Sabha & LSE |  | Green
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 945 | PRAYAGRAJ | 94502A | KAUNDHIYARA | 94501 | SHANKAR GARH | 94503008 | BEEKAR (NARAYANPUR) | EGE5370 | Sandhya Maurya | SUJAUNA (DANDUPUR) | Submitted for Approval | 05/03/2025 | SMC ( Full Day ) | P.S.POORE KINNAR | SMC | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92309A | NIGHASAN | 92309 | NIGHASAN | 92309005 | NAURANGABAD | EGE8764 | Anita Devi | HARDUWAHI | Approved | 26/02/2025 | GKP ( First Half ) | PRI.SCH. HARDUWAHI | GKP | 0 | No | No | 26/02/2025 | D2D Contact |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 971 | BHADOHI | 97107A | ABHOLI | 97105 | DEEGH | 97105207 | SITAMARHI | EGE7662 | Rohit Kumar | DEEGH | Submitted for Approval | 06/03/2025 | GKP ( Full Day ) | Composite School Deegh | GKP | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92206A | BANDA | 92214 | PUWAYA | 92214040 | NAGARIYA BUZURG | EGE8552 | Rohit Kumar Singh | SUNARA BUJURG | Approved | 28/02/2025 | D2D Contact ( First Half ) |  | D2D Contact | 7 | No | No |  |  |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 945 | PRAYAGRAJ | 94516A | MANDA | 94505 | MEJA | 94505028 | KOHARAR (KHIRAR) | EGE5366 | Sandeep Singh | GHORAHA | Approved | 05/03/2025 | SMC ( Full Day ) | PS GHORAHA | SMC | 0 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232411A | MEGHNAGAR | 232411 | MEGHNAGAR | 232411005 | PAVAGOI BADI | SMP272 | Anil Beberiya | TALAVALI | Approved | 03/02/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 12 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92314A | PASGAWAN | 92314 | PASGAWAN | 92308003 | LALHAUA | EGE8522 | Saraswati Devi | LALHAUA | Approved | 24/02/2025 | Bal Sabha & LSE ( Second Half ) | JHS LALHAUVA | Bal Sabha & LSE | 0 | No | No |  |  |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 945 | PRAYAGRAJ | 94504A | PRATAP PUR | 94515 | DHANUPUR | 94520065 | CHIRI (VEERBHANPUR) | EGE8894 | Km Ridima Yadav | PAKLOR | Approved | 18/02/2025 | D2D Contact ( Second Half ) |  | D2D Contact | 2 | No | No | 18/02/2025 | Meeting |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232412B | RANAPUR | 232412 | RANAPUR | 232412049 | BUDHASHALA | SMP261 | Pramod Kumar Meda | UBERAO | Submitted for Approval | 10/02/2025 | GKP ( First Half ) | GOVT P S UBERAO | GKP | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92208A | TILHAR | 92208 | TILHAR | 92208023 | BARHEPUR | EGE8547 | Shaved | SAMADHANA | Approved | 22/02/2025 | Bal Sabha & LSE ( First Half ) | JHS SAMDHANA | Bal Sabha & LSE | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92309A | NIGHASAN | 92309 | NIGHASAN | 92309005 | NAURANGABAD | EGE8764 | Anita Devi | BHEDAURI | Approved | 07/03/2025 | Bal Sabha & LSE ( First Half ) | JHS BHEDAURI | Bal Sabha & LSE | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92516A | KACHAUNA | 92516 | KACHAUNA | 92516013 | BARRAGHUMAN | EGE8307 | Avneesh Kumar | SUNNI | Approved | 28/02/2025 | GKP ( Full Day ) | Composite School SUNNI | GKP | 0 | No | No | 28/02/2025 | Enrolment |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92516A | KACHAUNA | 92516 | KACHAUNA | 92516023 | KHAJOHANA | EGE8083 | Brajendra Kumar | KAMIPUR | Approved | 18/02/2025 | Bal Sabha & LSE ( Second Half ) | Composite School KAMIPUR | Bal Sabha & LSE | 0 | No | No | 18/02/2025 | GKP |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92306A | LAKHIMPUR | 92306 | LAKHIMPUR | 92308037 | DARI | EGE8746 | Sandeep Kumar | KAKRAHA | Approved | 18/02/2025 | D2D Contact ( Second Half ) |  | D2D Contact | 12 | No | No | 18/02/2025 | D2D Contact GKP |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 970A | ROBERTSGANJ | 969 | MIRZAPUR | 97005A | CHATRA | 96906 | RAJGARH | 96906118 | GORTHARA | EGE7299 | Dhiraj Kumar |  | Submitted for Approval | 08/03/2025 | Leave ( Full Day ) |  | Leave | 0 | No | No
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 970A | ROBERTSGANJ | 970 | SONBHADRA | 97003A | ROBERTSGANJ | 97004 | GHORAWAL | 97004037 | MUDILADIH | EGE5030 | Maisar Ali |  | Approved | 21/02/2025 | Meeting ( Full Day ) |  | Meeting | 0 | Yes | No | 21/02/2025 | Meeting |  | Green
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2349A | ALIRAJPUR | 2349 | ALIRAJPUR | 234906A | SONDWA | 234906 | SONDWA | 234906092 | SILOTA | SMP210 | ARVIND KANESH | WAVI | Approved | 04/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 15 | No | No |  |  |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 971 | BHADOHI | 97107A | ABHOLI | 97105 | DEEGH | 97105018 | KALAPUR | EGE5376 | Dileep Kumar | CHAK MANDHATA | Approved | 26/02/2025 | GKP ( Full Day ) | P S CHAK MANDHATA | GKP | 0 | No | No | 26/02/2025 | Meeting |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 970A | ROBERTSGANJ | 969 | MIRZAPUR | 96911A | MARIHAN | 96911 | MARIHAN | 96911089 | ATAAREE (KUNDARUF) | EGE9069 | Rekha Kumari | KIRHA (RAMPUR THAKUR DAYAL) | Approved | 17/02/2025 | GKP ( Full Day ) | P.S. KIRHA | GKP | 0 | No | No | 17/02/2025 | Bal Sabha & LSE |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2325 | DHAR | 2325 | DHAR | 232506 | GANDHWANI | 232509 | NALCHHA | 232505057 | ANUPURABAHADRA | EGE6183 | Lalsingh Dodwe | TITIPURA | Submitted for Approval | 15/02/2025 | Enrolment ( Full Day ) | P.S. TITIPURA | Enrolment | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92507A | BABAN | 92507 | BABAN | 92507041 | MUJAHIDPUR | EGE8085 | Arun Kumar | BEHATA GOKUL | Approved | 19/02/2025 | GKP ( First Half ) | PRY. SCH. BEHATA GOKUL | GKP | 0 | Yes | Yes | 19/02/2025 | GKP |  | Green
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92206A | BANDA | 92207 | KHUTAR | 92207037 | RAMPUR KALA | EGE8278 | Sonam Devi | LAXMIPUR | Approved | 03/03/2025 | GKP ( Full Day ) | COMPOSIT LAXMIPUR | GKP | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92516A | KACHAUNA | 92515 | KOTHAWAN | 92515078 | MAMREJPUR | EGE8975 | Neetu Devi | ANTSAT | Submitted for Approval | 04/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 25 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92313A | RAMIYA BEHAR | 92313 | RAMIYA BEHAR | 92313010 | JATPURVA | EGE9044 | Tejasvi Mishra | SEMARI | Approved | 06/03/2025 | D2D Contact ( Second Half ) |  | D2D Contact | 10 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92513A | SANDI | 92514 | HARPALPUR | 92514005 | KAKRA | EGE9135 | Alok Kumar | KAKRAOA | Approved | 21/02/2025 | GKP ( First Half ) | PRY. SCH. FADULLAPUR | GKP | 0 | No | No |  |  |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 945 | PRAYAGRAJ | 94508A | BAHADURPUR | 94519 | BAHARIYA | 94508101 | RAM NAGAR | EGE5369 | Omprakash Yadav | MOTINAGAR (TEJPUR) | Approved | 28/02/2025 | Retention ( Second Half ) |  | Retention | 0 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232404A | THANDLA | 232404 | THANDLA | 232404116 | DEVKA | SMP278 | Dilip Bhuriya | GORIYAKHANDAN | Approved | 05/03/2025 | Enrolment ( Full Day ) | EGS MAL FALIYA GORIYA KHANDAN | Enrolment | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 922 | SHAHJAHANPUR | 92212A | MIRJAPUR | 92203 | JALALABAD | 92203007 | KANARI BANK | EGE9215 | Taniya | GORA MAHUA | Approved | 22/02/2025 | D2D Contact ( Second Half ) |  | D2D Contact | 10 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92509A | TANDIYAWA | 92509 | TANDIYAWA | 92509098 | GADDI PURWA | EGE6153 | Mohini Devi | GADDI PURWA | Approved | 07/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 25 | No | No
9B | UP ZONE-2 | UTTAR PRADESH | 9 | 924A | SITAPUR | 924 | SITAPUR | 92403A | BISWAN | 92403 | BISWAN | 92403076 | RAMKUND | EGE8659 | Upendra Kumar Verma | KORASA | Approved | 05/03/2025 | GKP ( Second Half ) | P.S. KAURASA | GKP | 0 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2327A | KHARGONE | 2327 | KHARGONE | 232713A | BADWAHA | 232712 | KASRAWAD | 232712047 | UMRIYA | SMP51 | Viswas Silawat |  | Approved | 24/02/2025 | Meeting ( Full Day ) |  | Meeting | 0 | Yes | No | 24/02/2025 | Meeting |  | Green
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 925A | HARDOI | 925 | HARDOI | 92516A | KACHAUNA | 92516 | KACHAUNA | 92516025 | MUSALMANABAD | EGE8493 | Sandeep Kumar | GAUSGANJ | Submitted for Approval | 07/03/2025 | D2D Contact ( First Half ) |  | D2D Contact | 8 | No | No
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2349A | ALIRAJPUR | 2349 | ALIRAJPUR | 234905A | UDAYGARH | 234905 | UDAYGARH | 234905077 | DEDARWASA | SMP221 | ANTAR SINGH DAWAR | LAKSHMAN FALIYA | Approved | 18/02/2025 | Enrolment ( Full Day ) | UG EGS RATMALIYA LAKSHAMAN F. | Enrolment | 0 | No | No |  |  |  | Red
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92314A | PASGAWAN | 92314 | PASGAWAN | 92308003 | LALHAUA | EGE8522 | Saraswati Devi | LALHAUA | Approved | 07/03/2025 | Bal Sabha & LSE ( Second Half ) | JHS LALHAUVA | Bal Sabha & LSE | 0 | No | No
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 971 | BHADOHI | 97104A | AURAI | 97104 | AURAI | 97104164 | VARI GANV | EGE9063 | Bhola Nath Dubey | NARTHUA | Approved | 24/02/2025 | GKP ( First Half ) | COMPOSITE SCHOOL NARTHUA | GKP | 0 | Yes | Yes | 24/02/2025 | GKP |  | Green
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92306A | LAKHIMPUR | 92308 | MITAULI | 92308069 | VISHOKHAR | EGE8999 | Sandeep Kumar | SEN PUR | Approved | 19/02/2025 | GKP ( Second Half ) | PS SENPUR | GKP | 0 | Yes | Yes | 19/02/2025 | GKP |  | Green
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 970A | ROBERTSGANJ | 970 | SONBHADRA | 97001A | CHOPAN | 97001 | CHOPAN | 97001104 | BANGANWA | EGE7835 | Sunil Kumar | GOTHANI | Submitted for Approval | 06/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 9 | No | No
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 970A | ROBERTSGANJ | 969 | MIRZAPUR | 96902A | HALIA | 96902 | HALIA | 96902146 | GURGEE | EGE6507 | Anshu Kumar | FULYAREE | Approved | 19/02/2025 | GKP ( Full Day ) | COMPOSIT SCHOOL FULIYAREE | GKP | 0 | Yes | Yes | 19/02/2025 | GKP |  | Green
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92306A | LAKHIMPUR | 92302 | BEHJAM | 92306062 | KESHAVPUR GURELA | EGE8512 | Jeetu Singh | LAGUCHA | Approved | 03/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 25 | No | No |  |  |  | Red
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232411A | MEGHNAGAR | 232411 | MEGHNAGAR | 232411064 | JHAPADRA | SMP264 | Balu Medha |  | Submitted for Approval | 12/02/2025 | Leave ( Full Day ) |  | Leave | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 919A | BUDAUN | 919 | BUDAUN | 91901A | QADARCHOWK | 91909 | USAWAN | 91909063 | SOODHEY MAI | EGE8370 | Brajesh Kumar | BACHELI DARANAGAR | Submitted for Approval | 21/02/2025 | GKP ( First Half ) | PS. BACHELI DARANAGAR | GKP | 0 | No | No
9C | UP ZONE-3 | UTTAR PRADESH | 9 | 922A | SHAHJAHANPUR | 923 | LAKHIMPUR KHERI | 92310A | NAKAHA | 92310 | NAKAHA | 92310015 | NAKAHA | EGE8762 | Arti Gupta | MANJHARA | Approved | 03/03/2025 | D2D Contact ( Second Half ) |  | D2D Contact | 15 | No | No |  |  |  | Red
9A | UP ZONE-1 | UTTAR PRADESH | 9 | 945A | PRAYAGRAJ | 971 | BHADOHI | 97107A | ABHOLI | 97105 | DEEGH | 97105018 | KALAPUR | EGE5376 | Dileep Kumar | CHAK MANDHATA | Submitted for Approval | 17/02/2025 | GKP ( Second Half ) | P S CHAK MANDHATA | GKP | 0 | No | No | 17/02/2025 | Bal Sabha & LSE
23 | MADHYA PRADESH | MADHYA PRADESH | 23A | 2324A | JHABUA | 2324 | JHABUA | 232410 | RAMA | 232410 | RAMA | 232410020 | PARA | SMP253 | Sanjay Bariya | REHANDA | Approved | 07/03/2025 | D2D Contact ( Full Day ) |  | D2D Contact | 6 | No | No