## OVERALL
Performance till current week
OUTCOME | Annual TGT- Original | REVISED-ANNUAL TGT [H2 Plan] | YTD Tgt | YTD ACH | Weekly tgt | Weekly ach. | BALANCE TGT
ENROLMENT
5 - 6 Years | 220778 | 139359 |  | 57530 | 0 | 1325 | 81829
7- 14 Years | 211802 | 109631 |  | 77457 | 0 | 1642 | 32174
Overall: 5-14 Years | 432580 | 248990 |  | 134987 | 17156 | 2967 | 114003
Achvt. % |  |  |  | #DIV/0! |  | 17.29%
RETENTION
# Girls Leaders- BS formation | 78930 | 60972 |  | 27812 | 10729 | 5949 | 33160
# SMC Members Trained | 64310 | 53941 |  | 20067 | 0 | 14 | 33874
#Retention Data Verification | 260971 | 260971 |  | 165254 | 22469 | 23560 | 95717
LEARNING
# Learning Beneficiaries-PO | 331875 | 245845 |  | 112700 | 0 | 2675 | 133145
Source | Ops | Ops | Ops sheet by Nitin | PMS | Ops | PMS
YTD Traget- Achv. Till nOv+Target till 2nd week of Jan
Note on G2: 3rd to 10th Jan
Note on H2: Sutapa: Revides annual target - YTD Achievement

## RAJASTHAN
|  |  | PSU |  | PSU
Performance till current week
ENROLMENT | Annual TGT- Original | REVISED-ANNUAL TGT [H2 Plan] | YTD Tgt | YTD ACH | Weekly tgt | Weekly ach. | BALANCE TGT
5 - 6 Years | 35884 | 30246 |  | 12387 | - | 682 | 17859
7- 14 Years | 31012 | 26139 |  | 17015 | - | 816 | 9124
RAJ : 5-14 Years | 66896 | 56385 |  | 29402 | 6885 | 1498 | 26983
Achvt % |  |  |  | #DIV/0! |  | 21.76%
15-18 Years [RSOS] | 7885 [5000-RSOS; 2885-Mainstream] | 5000 |  | 3306 | - | 0 | 1694
RETENTION
# Girls Leaders | 28457 | 26468 |  | 12615 | 6617 | 3641 | 13853
# SMC Members Trained | 21850 | 21850 |  | 8715 | 0 | 0 | 13135
#Retention Data Verification | 102728 | 102728 |  | 50221 | 10273 | 10014 | 52507
LEARNING |  |  |  | 48.89%
# Learning Beneficiaries-PO |  | 88892 |  | 22257 | 0 | 373 | 66635
# Learning Beneficiaries-AGP | 19100 | 19100 |  | 830 | 0 | 0 | 18270
| PSU |  | PSU |  | PSU |  | PSU | PSU
District | Retention | CBL Conversion % | High Risk error (Enrollment CV) | D2D Enrolments | D2D Enrolments per Cluster | %D2D
| Data collection % complete | Conversion from CBL (at least one session attended?) to Enrolment status (??) % | Sutapa to source from CV data | #of D2d enrolments with SR number | Average D2D enrolments per FC/cluster | % of D2D enrolments (with SR number And CIOOSG)
AJMER | 96% | 16.26% | 5% | 1714 | 45.1053 | 95.28%
BANSWARA | 29.55% | 34.8% | 8% | 4997 | 71.3857 | 99.17%
BHILWARA | 100% |  | 1% | 1335 | 47.6786 | 100%
BUNDI | 95.63% | 19.75% | 13% | 1507 | 65.5217 | 100%
JALORE | 83.46% | 56.29% | 6% | 3285 | 86.4474 | 99.97%
JHALAWAR | 97.98% | 38.1% | 8% | 805 | 18.2955 | 100%
RAJSAMAND | 47.32% | 22.71% | 5% | 1998 | 60.5455 | 79.19%
SALUMBER | 43.88% | 46.7% | 6% | 5154 | 112.0435 | 100%
SIROHI | 99.85% | 32.49% | 7% | 2745 | 56.0204 | 93.97%
UDAIPUR | 41.34% | 54.64% | 8% | 5862 | 91.5938 | 99.71%
Total | 41%(Target-102728, Achv-50221) | 40%(Enrolled Beneficiary-5824 , Current Year Enrolled D2D,CIOOSG,GSA Beneficiary- 2310) |  | 29402 | 67.903 | 97.2%
| Retention data collection completion % | CBL Conversion % | High-risk errors |  |  | D2D/ CIOOSG enrolments
Red | Less than 50% | Less than 40% | 10%+ |  |  | less than 60%
Amber | 50-75% | 40-60% | 8-10% |  |  | 60-90%
Green | 75%+ | 60%+ | less than 8% |  |  | >90%
*Pending analysis of OOSGs that have attended CBL but are not D2D/ CIOOSG
Note on C17: Administrator: Camp-1&2, Female ben enr./total ben

## MADHYA PRADESH
Performance till current week
OUTCOME | Annual TGT- Original | REVISED-ANNUAL TGT [H2 Plan] | YTD target | YTD ACH | Weekly tgt | Weekly ach. | BALANCE TGT
ENROLMENT
5 - 6 Years | 99299 | 52662 |  | 20033 | - | 505 | 32629
7- 14 Years | 109114 | 36183 |  | 27661 | - | 699 | 8522
MP: 5-14 Years | 208413 | 88845 |  | 47694 | 8438 | 1174 | 41151
RETENTION
# Girls Leaders | 21067 | 17342 |  | 5417 | 2540 | 1028 | 11925
# SMC Members Trained | 18520 | 16131 |  | 8949 | 0 | 0 | 7182
#Retention Data Verification | 87448 | 87448 |  | 71463 | 10734 | 10529 | 15985
LEARNING
# Learning Beneficiaries-PO | 96575 | 49736 |  | 35279 | 0 | 1697 | 14457
District | Retention | CBL Conversion % | High Risk (Enrollment CV) | D2D Enrolments | D2D Enrolments per Cluster | % of D2D enrolments (with SR number And CIOOSG)
ALIRAJPUR | 77.13% | 72.3% | 8% | 10139 | 98.3689 | 80.78%
BARWANI | 91.33% | 73.07% | 5% | 14011 | 140.11 | 76.61%
DHAR | 62.02% | 55.84% | 3% | 3619 | 78.6739 | 82.7%
JHABUA | 89.2% | 51.22% | 5% | 7912 | 76.0769 | 83.74%
KHALWA | 96.8% | 29.84% | 6% | 1865 | 186.5 | 100%
KHANDWA | 87.92% | 46.54% | 4% | 10148 | 100.4752 | 99.89%
Total | 82%(Target-87448, Achv.-71463 ) | 62%(Enrolled Beneficiary-6898 , Current Year Enrolled D2D,CIOOSG,GSA Beneficiary- 4255) |  | 47694 | 102.7737 | 84.14%

## UTTAR PRADESH
Performance till current week
OUTCOME | Annual TGT- Original | REVISED-ANNUAL TGT [H2 Plan] | YTD Target | YTD ACH | Weekly tgt | Weekly ach. | BALANCE TGT
ENROLMENT
5 - 6 Years | 67184 | 45433 |  | 18758 | 0 | 24 | 26675
7- 14 Years | 59401 | 36847 |  | 27352 | 0 | 47 | 9495
UP : 5-14 Years | 126585 | 82280 | 21797 | 46110 | 1065 | 71 | 36170
RETENTION
# Girls Leaders | 25974 | 13730 | 8228 | 5755 | 1572 | 13 | 7975
# SMC Members Trained | 19980 | 13320 |  | 464 | 0 | 0 | 12856
#Retention Data Verification | 50631 | 50631 |  | 34085 | 0 | 2 | 16546
LEARNING
# Learning Beneficiaries-PO | 1,12,980 | 86248 | 3692 | 44042 | 0 | 254 | 42206
Performance till current week (Sidhi)
OUTCOME | Annual TGT- Original | REVISED-ANNUAL TGT [H2 Plan] | YTD Target | YTD ACH | Weekly tgt | Weekly ach. | BALANCE TGT
ENROLMENT
5 - 6 Years | 18411 | 11018 |  | 6352 | 0 | 114 | 4666
7- 14 Years | 12275 | 10462 |  | 5429 | 0 | 110 | 5033
UP : 5-14 Years | 30686 | 21480 |  | 11781 | 768 | 224 | 9699
RETENTION
# Girls Leaders | 3432 | 3432 |  | 4025 | 0 | 1267 | -593
# SMC Members Trained | 3960 | 2640 |  | 1939 | 0 | 14 | 701
#Retention Data Verification | 20164 | 20164 |  | 9485 | 1453 | 3015 | 10679
LEARNING
# Learning Beneficiaries-PO | 28935 | 10560 |  | 11122 | 0 | 351 | -562
DISTRICT RANKING:
District | Retention | CBL Conversion % | High Risk (Enrollment CV) | D2D Enrolments | D2D Enrolments per Cluster | % of D2D enrolments (with SR number And CIOOSG)
CHITRAKOOT | 67% | 54.04% | 4% | 23261 | 106.7018 | 99.11%
FATEHPUR |  | 51.11% | 7% | 10739 | 61.3657 | 99.99%
PRAYAGRAJ |  | 43.19% | 9% | 2659 | 20.6124 | 100%
ROBERTSGANJ |  | 36.96% | 10% | 9451 | 69.4779 | 100%
SIDHI | 47% | 61.86% | 7% | 11781 | 89.25 | 99.88%
Total | 62%(UP + SIDHI Target - 70795 , Achv. -43750) | 50%(Enrolled Beneficiary-20098 , Current Year Enrolled D2D,CIOOSG,GSA Beneficiary- 10061) |  | 57891 | 73.2772

## WEEKLY
|  |  | Dec | [7 empty] | Jan
State | District | Outcome | Wk1 Target | Wk1 Ach | Wk2 Target | Wk2 Ach | Wk3 Target | Wk3 Ach | Wk4 Target | Wk4 Ach | Wk5 Target | Wk5 Ach | Wk6Target | Wk6 Ach | Wk7Target | Wk7 Ach | Wk8Target | Wk8Target
|  |  | Manual | PMS | Manual | PMS | Manual | PMS | Manual | PMS | Manual | PMS | Manual | PMS | Manual | PMS | Manual | PMS
|  | Enrolment 5-14 | 12440 | 5135 | 17156.2784 | 4378 | 21589.4914 |  | 20208.725
Retention
|  | # Girls Leaders | 8699 | 7282 | 10728.75 | 5949 | 18508.75 |  | 6687.05
# SMC Members Trained
|  | #Retention Data Verification | 22143.9 | 22111 | 22468.9 | 23560 | 25517.9 |  | 23810.9
Learning
|  | # Learning Beneficiaries-PO (Camp Vidya 2) | 0 | 10459 | - | 2675 | - |  | -

## TRENDS
Outcome | Enrolment
Weekly Achievment against target
State | District | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Insight
MP | D1 | -10% | -20% | -10% | -5% | -15% | -10% | D1 is consistently underperforming. Estimates may be unrealistic or support may be required.
| D2 | 10% | 15% | -10% | 10% | -5% | 5% | D2 performance is erratic and no pattern visible.
Quality - Trends in Quality Assessment (High-risk errors)
State | District | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Insight | Action Recommended
|  | YTD | YTD | YTD | YTD | YTD | YTD
MP | D1 | Green | Green | Amber | Amber | Red | Red | D1 quality assessment steadily getting worse | #of matching errors is of concern. Analyse by FC and provide support to improve
| D2 | Amber | Red | Red | Red | Amber | Amber | D2 quality assessment steadily getting better
| D3 | Green | Amber | Amber | Amber | Amber | Amber | D3 quality is within acceptable thresholds but could be improved

## DEFINITIONS
Cut off date | YTD-Till 16th Jan 2021, Weekly- 10 Jan 2022 to 16th Jan 2022 | Cut off date | Same cutoff date as Monday morning Enrolment report i.e. data as at Sunday
Enrollment | # OOSG 5-14, class 1-8, current program year, complete SR but only D2D,GSA and CIOOSG. | Enrollment | # OOSG 5-14, class 1-8, current program year, complete SR with all flags, D2D/CIOOSG/GSA; separately OOD2D %
# Girl Leaders | # All registered girls where Bal Sabha Formation status is Bal Sabha Formed | # Girl Leaders | # All registered girls where Bal Sabha Formation status is Bal Sabha Formed and activity is approved by IO
# SMC Members Trained | # Members trained and activity approved by IO + Community Level SMC Meeting's Member | # SMC Members Trained | # Members trained and activity approved by IO (include Community LS - will be reported?)
Retention Data Collection | # Verified OOSC | Retention Data Collection | # Verified OOSC
Retention% | # Verified OOSC/Targeted OOSC | Learning Beneficiaries | # Beneficiaries ( both girls and boys) who attended at least one CBL session in either Camp 1 or 2 or both.
Learning Beneficiaries | # Beneficiaries ( both girls and boys) who attended at least one CBL session in either Camp 1 or 2 or both. Weekly from Session 1 Attendance(last 7 Days) | Retention Data Collection % Complete | # Verified OOSC against Total Retention Target for current program year
CBL Conversion% | # Learning beneficiaries who got enrolled this program year against D2D/CIOOSG # Learning beneficiaries | CBL Conversion | # Learning beneficiaries who got enrolled this program year against D2D/CIOOSG # Learning beneficiaries
% D2D Enrolments | # (D2D + CIOOSG + GSA) against # OOSG whose matching is not pending- Quality Enrolment Girls | % D2D Enrolments | # (D2D + CIOOSG + GSA) against # OOSG whose matching is not pending
| Where age: 5-14, class: 1-8, SR: Complete, Enrolment Year: Current program year |  | Where age: 5-14, class: 1-8, SR: Complete, Enrolment Year: Current program year
D2D Enrolments per FC | Average # (D2D + CIOOSG + GSA) Girls enrolments per FC | D2D Enrolments per FC Average # (D2D + CIOOSG + GSA) enrolments per FC